## Index
Project Plan

	Document Version	1.9
	Name	Role	Signature	Date 06/12/2011
	Prepared/Updated by:

Revision History
Version No	Date	Author		Comment

					1.6	03/09/11	Shanmugarajan				1.6	03/09/11	Shanmugarajan				1.6	03/09/11	Shanmugarajan				1.6	03/09/11

## Sheet1
Delivery/Weeks		Week 1			saturday	sunday			Week 2			saturday	sunday			Week 3			saturday	sunday			Week 4			saturday	sunday	Week 5
	13-12-2011	14-12-2011	15-12-2011	16-12-2011	17-12-2011	18-12-2011	19-12-2011	20-12-2011	21-12-2011	22-12-2011	23-12-2011	24-12-2011	25-12-2011	26-12-2011	27-12-2011	28-12-2011	29-12-2011	30-12-2011	31-12-2011	01/01/11	02/01/11	03/01/11	04/01/11	05/01/11	06/01/11	07/01/11	08/01/11	09/01/11

Wire-frame Analysis

Use-Case Document

Result Framework Document(RFD)

ER-Diagram

Development Process

Test Case-BDD

Project Review with Mentor

Heroku Deployment

Final Release

VERSION 1.0.0 - Wire-frame Analysis
Use-Case Document
Result Framework Document(RFD)
ER-Diagram
Development Process
Test Case-BDD
Project Review with Mentor
Heroku Deployment
Final Release

## Sheet2
Development		Week 1			saturday	sunday					saturday	sunday					saturday
	20-12-2011	21-12-2011	22-12-2011	23-12-2011	24-12-2011	25-12-2011	26-12-2011	27-12-2011	28-12-2011	29-12-2011	30-12-2011	31-12-2011	01/01/12	02/01/12	03/01/12	04/01/12	05/01/12	06/01/12	07/01/12

Database Creation and Relationship

Design phase

Sign-in and Sign-up page

Admin module

Ticket module

Department module

Staff and News module

Client and FAQ module

validation

Database Creation and Relationship
Design phase
Sign-in and Sign-up page
Admin module
Ticket module
Department module
Staff and News module
Client and FAQ module
validation

## Sheet5
Phase I – My Settings Feature Implementation
Start date	20/12/11
End date	06/01/12

MODULE	Subtasks	Start Date	End Date	Status

Layout integration		20/12/11	22/12/11	Completed
	Devise registration	23/12/11	23/12/11	Completed
Admin	Insert and update Staff	23/12/11	23/12/11	Completed
	Insert and update client	23/12/11	23/12/11	Completed
	Update admin account details	23/12/11	23/12/11	Completed
	Insert and update departments	26/12/11	26/12/11	Completed
	Submit and Assign tickets	26/12/11	26/12/11	Completed
Ticket	Update ticket status	27/12/11	27/12/11	Completed
	CRUD operation on tickets	27/12/11	28/12/11	Completed
Department	CRUD operation on departments	29/12/11	29/12/11	Completed
Login	Sign-in and Sign-up(for staff,client)	30/12/11	30/12/11	Completed
Staff	Update account details	02/01/12	02/01/12	Completed
	update operation on tickets	02/01/12	02/01/12	Completed
News	Adding,Editing and displaying the news by admin	03/01/12	03/01/12	Completed
Client	CRUD operation on tickets	04/01/12	04/01/12	Completed
	Account details	04/01/12	04/01/12	Completed
FAQ	Adding questions and comment for that questions	04/01/12	04/01/12	Completed
Validations	all over forms	05/01/12	05/01/12	Completed
Test Cases	BDD-rspec	05/01/12	05/01/12	Completed
Heroku Deplayement		06/01/12	06/01/12	Completed
Demo		08/01/12