## Sheet1
Phase I – My Settings Feature Implementation
Start date	20/12/11
End date	06/01/12

MODULE	Subtasks	Start Date	End Date	Status

Layout integration		20/12/11	22/12/11	Completed
	Devise registration	23/12/11	23/12/11	Completed
Admin	Insert and update Staff	23/12/11	23/12/11	Completed
	Insert and update client	23/12/11	23/12/11	Completed
	Update admin account details	23/12/11	23/12/11	Completed
	Insert and update departments	26/12/11	26/12/11	Completed
	Submit and Assign tickets	26/12/11	26/12/11	Completed
Ticket	Update ticket status	27/12/11	27/12/11	Completed
	CRUD operation on tickets	27/12/11	28/12/11	Completed
Department	CRUD operation on departments	29/12/11	29/12/11	Completed
Login	Sign-in and Sign-up(for staff,client)	30/12/11	30/12/11	Completed
Staff	Update account details	02/01/12	02/01/12	Pending
	update operation on tickets	02/01/12	02/01/12	Pending
	Add/view by client,admin,staff Comment for tickets	03/01/12	03/01/12	Pending
Client	CRUD operation on tickets	04/01/12	04/01/12	Pending
	Account details	04/01/12	04/01/12	Pending
	Submit tickets	04/01/12	04/01/12	Pending
Validations	all over forms	05/01/12	05/01/12	pending
Attachment	Paperclip	05/01/12	05/01/12	Pending
Demo		06/01/12